STRATEGY DELIVERY PLAN 2026 - 7

1.0	Purpose

1.1	The purpose of this report is to detail the Council’s plans to implement the third phase of its four-year strategy.

2.0	Background

2.1	At its meeting on 4 June 2024 Modbury Parish Council adopted a new strategy for the period 1 April 2024 to 31 March 2028.

2.2	It set out the Council’s vision for the parish, the values which underpin the vision, an assessment of the Council’s strengths, weaknesses, opportunities and challenges, its priorities and its key objectives. It proposed that implementation would be through a series of annual delivery plans of which this is the third.

3.0	Delivering the strategy for 2026-7

3.1	This plan identifies the work and initiatives to be carried out, the objectives to be addressed by each (using the reference numbers in the strategy document), the individuals responsible for their delivery and the finance made available to support their implementation. It is envisaged that the plan will also form the basis of an annual report on outcomes achieved at the end of the current year.

3.2	Administration and finance

3.2.1	The Council will continue to administer its duties and responsibilities as effectively, economically and efficiently as possible, ensuring that it follows all legal and government requirements and guidelines.

3.2.2	In particular, it will ensure that it effectively discharges its responsibilities as sole trustee of Modbury Recreation and Sports Trust (MRST), the new charity tasked with managing and developing the Council’s sports facilities at the QE2 Recreation Ground.

3.2.3	The Council will continue to monitor the implementation of unitary local government, taking steps to ensure that the community is aware of the implications for local services and that, as far as possible, their interests are safeguarded.

3.2.4	In order to equip the Council and the Parish Clerk with the necessary skills to address the more challenging regulatory and administrative framework within which it will operate, greater emphasis will be placed on training. In particular the Clerk will be supported to achieve the Certificate in Local Council Administration qualification.

3.2.5	The Council’s Emergency Plan will be reviewed and overhauled by the Emergency Planning Working Group set up last year. The new plan will be adopted before the end of the current year and will incorporate any statutory requirements which become necessary following the implementation of Martyn’s Law (the outcome of the inquiry into the Manchester Arena terrorist bombing of 2017).

3.2.6	Strategic objectives: A1, A2, A3, C3, D3, D4, E3, E4, E5, E6, F3, F4, G1, G2, G3, G4, G5, G6, G7 and G8.

3.2.7	Responsible person/committee: Parish Clerk, Chair of Council, Chair of Finance, Finance and HR Committee, Emergency Planning Working Group.

3.2.8	Budgets: Staff salaries - £21,218, training - £2,000, audit - £750, administration - £4,390, professional fees - £2,000, insurances - £2,500, MRST - £2,500. Total £35,358.

3.3	Asset management

3.3.1	The Council will continue a programme of maintenance for all its land and built assets including its office and store, its three play parks, public open spaces including Palm Cross Green, Palm Cross allotments, the Millennium Meadow/Wood and the Galpin St Community Orchard, public benches, allotments, sports facilities and its two car parks.

3.3.2	Having been given the opportunity by South Hams District Council (SHDC) to bid for the permanent transfer of non-commercial land assets, the Council will aim to complete the process during the next 12 months.

3.3.3	This is the final year of the Council’s five-year grass cutting contract with Arborcure Ltd. We will, by the end of the year, undertake a tendering exercise and let a new term maintenance contract for this purpose, ensuring that any new land holdings are incorporated.

3.3.4	The Council will also undertake a tree survey in the autumn of 2026 to ensure that all trees on its land holdings are, as far as practicable, safe for the general public and adjoining owners

3.3.5	The Council has identified the need for mechanical assistance to undertake the maintenance of paved surfaces such as its two car parks and the network of highways footways which are no longer maintained by the two principal authorities. We will continue to explore options for the financing, storage and operation of a road clearing machine with a view to commencing a programme of works before the end of the year.

3.3.6	Strategic objectives: C2, E1, E2 and E3.

3.3.7	Responsible person/committee: Chair of Maintenance, Maintenance Committee, MARS.

3.3.8	Budgets: Premises costs - £11,250, maintenance - £18,200, defibrillators - £980, capital assets (MRST) - £5,000, Parking areas maintenance - £1,800. Total £37,230.

3.4	Town and countryside improvement

3.4.1	The Council will continue to support initiatives to improve the built and natural environment of the town and its surroundings, including the newly re-established Modbury Town Improvement Charity.

3.4.2	The Council’s newly constituted Heritage Working Group will supplement this approach by pursuing initiatives to preserve and celebrate the town’s heritage including its many listed buildings and ancient spaces.

3.4.3	Strategic objectives: A3, C1, C2, C3, E3, E5, F3, F7 and G1.

3.4.4	Responsible person/committee: Chair of Planning, Planning Committee, Heritage Working Group

3.4.5	Budgets: None. Total -Nil

3.5	Development control

3.5.1 	The Council will continue to comment on all planning applications within, and adjoining, the parish boundaries in accordance with SHDC time limits, assessing all proposals against the Council’s adopted Neighbourhood Plan as well as the Joint Local Plan (JLP). It will also monitor new developments in the parish to ensure they comply with planning consent conditions.

3.5.2	Having objected to and opposed the major application submitted by Bloor Homes during the last year, we have now submitted a complaint about the planning authority’s planning process to the Local Government Ombudsman. We have also commissioned a highways consultant to provide a professional assessment of the weaknesses in the original application. We will continue to pressurise SHDC to withdraw or at least reconsider their decision to grant outline permission.

3.5.3	SHDC has indicated that it proposes to consultation on a new JLP from July 2026 onwards and the Council will engage with this exercise to ensure that future development is appropriate for Modbury in terms of location, scale and mix.

3.5.4	At an appropriate juncture, probably once the new JLP has been approved, the Council will review its own Neighbourhood Plan.

3.5.5	Strategic objectives: A1, A2, C1, D4, F1, F2, F3, F4 and F7.

3.5.6	Responsible person/committee: Chair of Planning, Planning Committee.

3.5.7	Budgets: none. Total – nil.

3.6	Housing and regeneration

3.6.1	The Council will continue to lobby for greater investment in affordable housing, for specific developments for older people in the community and for those heritage sites which are currently at risk - in particular the old Baptist Chapel in Church St. In addition, we will seek to increase the supply of social housing associated with any large scale developments.

3.6.2	It will also ensure that any development contributions from S106 or Community Infrastructure Levy sources are utilized for the maximum benefit of Modbury parishioners.

3.6.3	Strategic objectives: A1, A2, C1, E1, E2, F1, F2, F3, F5, F6 and F7.

3.6.4	Responsible person/committee: Chair of Planning, Planning Committee, Heritage Working Group.

3.6.5	Budgets: none. Total – nil.

3.7	Sustainability

3.7.1	The Council will continue to develop its Climate and Environmental Plan for the parish, identifying ways in which the community’s carbon footprint can be reduced.

3.7.2	The Council will continue to support the efforts of Modbury Wildlife Action Group (MODWAG) in its mission to increase the biodiversity of the local environment.

3.7.3	It will also continue to work with surrounding parishes and community groups on the River Erme to address environmental and biodiversity issues affecting the waterways.

3.7.4	We will continue to work with other agencies to address flooding at Orcheton and, in particular, we will work with South West Water to help manage the planned town centre drainage works scheduled to start later in 2026.

3.7.5	Strategic objectives: A3, B2, B3, B5, C1, C3, D1, D2, D3, D4, E3, F3 and G1.

3.7.6	Responsible person/committee: Sustainability Working Group

3.7.7	Budgets: Sustainable Modbury - £1,000. Total £1,000.

3.8	Transport, road and path networks

3.8.1	The Council will continue to discharge its responsibilities under the Devon County Council (DCC) Road Warden and Public Paths Partnership schemes. The pothole repair and drainage teams will aim to improve on their outputs for last year and the newly re-constituted P3 maintenance team, having recently set up improved communications with DCC, will seek to improve the overall condition of the public paths network throughout the parish.

3.8.2	The Council will also lobby DCC to improve road surface conditions, particularly on the A379 and the worst of the minor road network, and public transport links in the parish and beyond. We will also continue to lobby for 20mph speed limits and improved street lighting on appropriate roads within the town of Modbury.

3.8.3	Strategic objectives: B1, B3, B4, B5, B6, B7, C1 and F3.

3.8.4	Responsible person/committee: Road Warden, P3 Coordinator, Chair of Maintenance, Maintenance Committee.

3.8.5	Budgets: none. Total – nil.

3.9	Community engagement and partnership working

3.9.1	The Council will continue to support community initiatives to improve the built and natural environment of the town and its surroundings such as Marvellous Modbury Makeover, Marigolds Day, Millennium Meadow Committee, Galpin St Community Orchard Committee, Modbury Bloomers, Modbury Litter Pickers and Modbury History Society, harnessing the skills and efforts of volunteers.

3.9.2	The Council will also engage with local traders and the Chamber of Commerce.

3.9.3	We will continue to pursue various local initiatives such as improved facilities for young people, a community fridge, a dementia friendly town and new measures to attract visitors based on the rich history of the town. In particular, we will finalise and implement our plans for the old telephone box in Poundwell as either an art installation or mini-museum.

3.9.4	The Council will also aim to improve its links with other local and principal authorities to benefit the parishioners of Modbury and seek to maximise their contribution to the cost of service delivery within the parish.

3.9.5	Strategic objectives: A1, A2, A3, A4, C1, C2, C3, D2, D3, E3, E4, E5, E6, G1, G2, G3, G5, G7 and G8.

3.9.6	Responsible person/committee: Community Engagement Working Group, Heritage Working Group.

3.9.7	Budgets: Grant awards - £2,000, Community engagement/marketing - £500. Total £2,500.

4.0 	Financial implications

4.1	The budget for 2026/7 was approved by Council on 6 January 2026 (Minute 2025 174).

4.2	The total budget allocation to support the delivery of the new strategy during 2026/7 is £76,088.

4.3	After allowing for grant and other income of £4,815, the net cost of the programme is £71,273 this is to be funded by precept income and bank interest totalling £69,150 plus transfers from reserves totalling £2,123.

5.0	Risk implications

5.1	The main risk associated with this plan is that lack of volunteer support is likely to lead to under-delivery of the programme.

5.2	This is particularly true of the Council itself which is currently carrying four Councillor vacancies.

5.3	Continued efforts will be necessary to try and increase the capacity of the Council to deliver and regular monitoring will be undertaken to identify and address any shortfall in delivery.

6.0	Recommendation

6.1	Council is recommended to approve this report and the Strategy Delivery Plan for 2026/7.

Modbury Parish Council Strategy Delivery Plan 2026/7: Approved 7 July 2026

PS/V1.1/26.06.26